## Summary
DO NOT DELETE
SUMMARY OF PROJECT CHANGES
|  |  |  | 2% | 5% | 15% | 0% | 5% | 6% | Rev 00
| COST PLAN BASIS |  | Nett Trade | Construction Contingency | Design Contingency | Prelims | Fees | OH&P | Inflation | GROSS TOTAL
| Cost Plan Stage ? |  | 100000000 | 2000000 | 5000000 | 16050000 | 0 | 6152500 | 7752150 | 136954650
| CAT | CATEGORY DESCRIPTION
| CA | Client Approved Scope Changes | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!
| CA-R | Regulatory Change | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | A | Approved
| DD | Design Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | P | Pending
| PA | Pricing / Measurement Adjustments | 500 | 10 | 25 | 80.25 | 0 | 30.7625 | 38.7608 | 684.7733 |  | R | Rejected
| EW | Early Warning | 700 | 14 | 35 | 112.35 | 0 | 43.0675 | 54.2651 | 958.6825 |  | T | Tenant
| VA | Value Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | WIP | Work In Progress
|  | UPDATED COST PLAN (INCLUDING APPROVED CHANGES AS PER SCHEDULE 1) | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!
Changes not yet approved or rejected
| P | Pending decision | 1100 | 22 | 55 | 176.55 | 0 | 67.6775 | 85.2736 | 1506.5012
| WIP | Work in Progress - Initial view of cost included | 500 | 10 | 25 | 80.25 | 0 | 30.7625 | 38.7608 | 684.7733
| R | Rejected change | 1000 | 20 | 50 | 160.5 | 0 | 61.525 | 77.5215 | 1369.5465
|  | Total including Approved, Pending and WIP Changes - excluding Rejected Changes | [7 empty] | #REF!
| CATEGORY | SUMMARY BY CATEGORY | [8 empty] | Do not Delete
| CA | Client Scope Changes | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!
| A | Approved | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | CA-A
| R | Rejected | 1000 | 20 | 50 | 160.5 | 0 | 61.525 | 77.5215 | 1369.5465 | CA-R
| WIP | Work In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CA-WIP
| P | Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CA-P
| CR | Regulatory Changes | 300 | 6 | 15 | 48.15 | 0 | 18.4575 | 23.2564 | 410.8639
| A | Approved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CR-A
| R | Rejected | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CR-R
| WIP | Work In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CR-WIP
| P | Pending | 300 | 6 | 15 | 48.15 | 0 | 18.4575 | 23.2564 | 410.8639 | CR-P
| DD | Design Development | 500 | 10 | 25 | 80.25 | 0 | 30.7625 | 38.7608 | 684.7733
| A | Approved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DD-A
| R | Rejected | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DD-R
| WIP | Work In Progress | 500 | 10 | 25 | 80.25 | 0 | 30.7625 | 38.7608 | 684.7733 | DD-WIP
| P | Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DD-P
| PA | Pricing / Measurement Adjustments | 500 | 10 | 25 | 80.25 | 0 | 30.7625 | 38.7608 | 684.7733
| A | Approved | 500 | 10 | 25 | 80.25 | 0 | 30.7625 | 38.7608 | 684.7733 | PA-A
| R | Rejected | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PA-R
| WIP | Work In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PA-WIP
| P | Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PA-P
| EW | Early Warning | 700 | 14 | 35 | 112.35 | 0 | 43.0675 | 54.2651 | 958.6825
| A | Approved | 700 | 14 | 35 | 112.35 | 0 | 43.0675 | 54.2651 | 958.6825 | EW-A
| R | Rejected | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EW-R
| WIP | Work In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EW-WIP
| P | Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EW-P
| VE | Value Engineering | 800 | 16 | 40 | 128.4 | 0 | 49.22 | 62.0172 | 1095.6372
| A | Approved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | VE-A
| R | Rejected | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | VE-R
| WIP | Work In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | VE-WIP
| P | Pending | 800 | 16 | 40 | 128.4 | 0 | 49.22 | 62.0172 | 1095.6372 | VE-P
TOTAL |  |  | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!

## Register
| Cost Tracker post Design Stage? | [13 empty] | REV 00
Change No | PM Tracker No. | Date | Location | Brief Description | Nett Trade | Construction Contingency | Design Contingency | Prelims | Fees | OH&P | Inflation | Gross Total | Status | Cat | Programme Impact
[6 empty] | 2% | 5% | 15% |  | 5% | 6%
1 | PM01 | 2016-05-18 | Block 1 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | A | CA | Yes | CA-A | CD-T
2 | PM03 | 2016-05-18 | Block 1 | #REF! | 1000 | 20 | 50 | 160.5 |  | 61.525 | 77.5215 | 1369.5465 | R | CA | No | CA-R | CD-T
[5 empty] | 500 | 10 | 25 | 80.25 |  | 30.7625 | 38.7608 | 684.7733 | WIP | DD |  | DD-WIP | CD-A
[5 empty] | 300 | 6 | 15 | 48.15 |  | 18.4575 | 23.2564 | 410.8639 | P | CR |  | CR-P | DD-T
[5 empty] | 500 | 10 | 25 | 80.25 |  | 30.7625 | 38.7608 | 684.7733 | A | PA |  | PA-A | CD-R
[5 empty] | 700 | 14 | 35 | 112.35 |  | 43.0675 | 54.2651 | 958.6825 | A | EW |  | EW-A | DD-A
[5 empty] | 800 | 16 | 40 | 128.4 |  | 49.22 | 62.0172 | 1095.6372 | P | VE |  | VE-P | CD-WIP
[5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | CA |  | CA- | DD-A
[5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | CA |  | CA- | DD-A
[5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | CA |  | CA- | DD-A
[5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | CA |  | CA- | DD-R
[5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | CA |  | CA- | DD-R
[5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | CA |  | CA- | DD-R
[5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | CA |  | CA- | PA-A
[5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | CA |  | CA- | DD-R
[5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | CA |  | CA- | DD-A
[5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | CA |  | CA- | DD-R
[5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | CA |  | CA-
[5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | CA |  | CA-
[5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | -
TOTAL |  |  |  |  | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!
Warning ! |  |  |  | Do not delete below this row. | [6 empty] | Check against summary | #REF!
Status list | Definition |  |  |  | Category |  |  |  |  | Programme Impact
A | Approved -Quintain has accepted change |  |  |  | CA | Client Approved Scope Changes |  |  |  | Yes | Programme Impact anticipated
R | Rejected - Quintain has rejected proposed change |  |  |  | CR | Regulatory Change |  |  |  | No | No anticipated programme impact
WIP | Work in Progress -Cost Impact of Change currently being assessed |  |  |  | DD | Design Development
P | Pending -Cost assessed and decision awaited |  |  |  | PA | Pricing Adjustment
| Blank |  |  |  | EW | Early Warning
[5 empty] | VE | Value Engineering
Blank